## FIPR version for Short programs
This document is designed to help you comprehend and manage the Final Internal Performance Review (FIPR). The FIPR process is comprises of activities organized in four phases (note: some activities in two phases happen concurrently). The phases are 1) preparation, 2) inception, 3) conducting the FIPR-part 1, and 4) conducting the FIPR-part2 If at any point you feel the need for guidance or support, please don't hesitate to submit a JIRA ticket using the Evidence and Learning support tool. |  |  | Evidence and Learning support tool link
Steps | FIPR Generalized Events (V2) for Short Program | Notes for FIPR toolkit user | Status
Phase 1: Preparation for the FIPR Complete phase 1 within a 30-day time frame (from the start date); this does NOT require 30 days of work Remember that some steps happen concurrently |  | NOTE: if you complete phase 1 in less than the 30 days time frame, you will have more time to complete the phases 2, 3 and 4 | Keep updating the status for each step | Started
1 | Familiarize yourself and team with all the tools in the FIPR Toolkit; carefully read the contents of the SOW template | Watch FIPR Toolkit introduction video https://mercycorpsemea.sharepoint.com/:v:/s/PaQHQ/EZ2lL1w9qlxLhkGejgZYkrMBFXWleFswBd1lzTV2GHWRjw?e=XIdsD9 |  | In progress
2 | Identify the Program Point-of-Contact (PPoC); the FIPR-Point-of-Contact (FIPR-PoC); |  |  | Behind the schedule
3 | Schedule and Hold FIPR KICK-OFF CALL (walk through generalized events, tools, examples) Your audience: Program team and involved partners >> Decide if you want external support to co-conduct the FIPR | Most programs should be able to conduct their FIPR without external assistance but larger, long-duration programs should consider getting support (and budgeting for this). Support can be from Regional/HQ direct costing or from external firms. Some support can be provided, at no cost, by the country or regional or HQ offices based on experience with FIPR and availability. Verify you have the financial resources needed. |  | Completed
4 | Submit a Jira Ticket for support from HQ or Regional staff (Mercy Corps only) >> ONLY IF YOU DECIDED YOU WANT HELP
5 | Watch video on Key Interventions identification; only if needed, schedule help session, using above link to submit JIRA ticket | Check Coffee Cha hour video link here https://mercycorpsemea.sharepoint.com/:v:/s/PaQHQ/ES9CFplL9p1NhHnwptT7cXcB8mDbb-6rBdwk_pr112KGsw?e=MQW9kb
6 | Create FIPR folders and organize files (not links, not 'draft' documents) | See FIPR Folder Struture and files tool https://library.mercycorps.org/record/46464 for suggested file folder organization
7 | Verify that the IPTT (spreadsheet version) is accurate and up-to-date.
8 | Verify that TolaData is complete AND verify it agrees with your spreadsheet version of your IPTT (if you have one)
9 | Verify events/shocks inventory is up-to-date | If such an inventory does not exist, document events and shocks that happened during the program implementation using FIPR Inventory of Events & Shocks tool https://library.mercycorps.org/record/46466
10 | Verify that inventory of deliverables is up-to-date (this is more detailed than the table listing deliverables in the SOW) | If such an inventory does not exist, document all program deliverables using using FIPR Inventory of Deliverables tool https://library.mercycorps.org/record/46465
11 | Complete your FIPR SOW
12 | Develop and release proposal for external support ; ONLY IF YOU DECIDED YOU NEED EXTERNAL SUPPORT
Phase 2: Inception of the FIPR Complete phase 2 within a 30-day timeframe from the end of phase 1; this does NOT require 30 days work Remember that some steps happen concurrently |  | NOTE: if you complete phase 2 in less than the 30 days time frame, you will have more time to complete the phases 3 and 4
1 | Read through, carefully, the contents of the FIPR Inception Report template
2 | Watch video on customizing Actuals vs Targets template: schedule help session if you need | Cha-Coffee hour session Link: https://mercycorpsemea.sharepoint.com/:v:/s/PaQHQ/EY8tDZ5Wb_BJqy1XgXUqjQwBpa2teUPOPslnLEE42Agw0w?e=ndUUXd
3 | Verify files/documents are their final versions and verify they are provided/accessible to those who need them.
4 | Review the documents and IPTT and make notes to draw from during SGDs and synthesis
5 | Select one of the two Actuals vs Targets templates and ADAPT it to your programs Result Framework | There is a 4-level assessment and a 5-level assessment that users can adapt for long-duration programs and short-duration programs. Check the link https://library.mercycorps.org/record/45853 to download the Actual vs.Targets template and guide, this will allow you to select the relevant template to your program
6 | Transpose your IPTT into your (customized) Actuals vs Targets template
7 | Estimate missing data points | There are, sometimes, endline data points that have not yet been collected when completing the FIPR, you estimate those missing points and later update with actual values
8 | SCORE the Actuals vs Targets template
9 | Complete your inception report
10 | Identify the Key Informants and SCHEDULE the KIIs for interviews regarding Operations (program staff and country office staff) | Ranges from 2-5 KII
11 | Identify the Key Informants and SCHEDULE the KIIs (or SGDs) for interviews regarding GEDSI | Ranges from 2-3 KII (2-3 if Mercy Corps staff only; if sub-contractors involved, Use SGDs instead of KIIs)
12 | Schedule SGD with MEL team on strengths/weaknesses of MEL system | Can add field staff remotely or bring them in to central program office
13 | Schedule the IPTT-focused SGDs with staff and key partners | Typical results frameworks have 3-6 components under the Goal/impact statement so # of SGD is 3-6)
14 | Schedule Key Intervention focused SGDs with staff and key partners | Short programs have <= 10 Key interventions so the maximum # of SGD is 10; long, complex programs have <= 15 Key interventions, so maximum #SGD = 15. These are doing concurrently by grouping them so they can be completed in one day or less
15 | Adapt existing or develop topical outline for KIIs
Phase 3: Conducting the FIPR Part 1 (progress assessment and KIIs) complete phase 3 within a 15-day timeframe from the end of phase 2 Remember that some steps happen concurrently |  | NOTE: While it is recommended that Phase 3 be conducted before Phase 4, they can be done concurrently if your team is large enough and has the time available.
1 | Read through, carefully, the contents of the FIPR Report template
2 | Document if the Results Framework (RF) changed during the life of the project; if yes, why?
3 | Document workplan completion
4 | Summarize work plans' completion, inclusion of GEDSI, and addressing sustainability | After each reporting period (used in the Actuals vs Targets), you should be able to say what percent of the activities were a) completed b) in progress (and usually carried over) or not yet started
5 | Review and summarize spending against the budget (BvA);
6 | Review and summarize learning plan and reports from quarterly review sessions and other learning (and adaptations) documents
7 | Complete section 3 of FIPR report (Results of Progress Assessment)
8 | Summarize what you found through analysis of context variables , qualitative monitoring, and internal indicators | Adding depth to your inventory and deliverables, use context variables, qualitative monitoring and internal indicators to enhance understanding on how your targets and interventions are affected
9 | Conduct Operations-focused KIIs (remote or in-person); take time to review, complete interview notes | These can be done remotely
10 | Conduct GEDSI-focused KIIs (remote or in-person) take time to review, complete interview notes | These can be done remotely
11 | Conduct MEL team discussion on strengths/weaknesses of MEL system (can be done remotely) | It is preferred to conduct this in phase 3 but could be done in phase 4
12 | Review documentation and summarize how safeguarding/accountability conducted during program implementation
Phase 4: Conducting the FIPR Part 2 (Performance Assessment and SGDs) complete phase 4 within a 15-day timeframe from the end of phase 3 ALL STEPS IN PHASE 4 ARE SEQUENTIAL |  | NOTE: While it is recommended that Phase 3 be conducted before Phase 4, they can be done concurrently if your team is large enough and has the time available.
1 | Review the remaining FIPR steps with leadership and send invitations for remote participation (MC and non MC)
2 | Conduct 1st of two rounds of SGDs. The 1st round uses the Actuals vs. Targets template with scores and reviews of project performance: one team at a time.
3 | Review and clean your notes from each of the (first round) SGDs around the Actuals vs Targets template with scores
4 | Conduct the 2nd round of SGDs - around the program's key interventions
5 | Review and clean the summary tables completed during the SGDs around key interventions
6 | Review and clean notes from MEL team discussion and exercise on strengths/weaknesses of MEL system
7 | Draft the FIPR Report
8 | Prepare a slide deck and disseminate the preliminary results while you incorporate feedback from debrief
9 | Finish the FIPR report (for internal distribution)
10 | Redact the FIPR report (for external distribution) | PPOC must read and approve external report before dissemination

## drop list (hidden)
Started
In progress
Completed
Behind the schedule